## Sheet1
Project Governance |  | Project Outputs |  | Project Approach:
Comment: | Action: | Comment: | Action: | Comment: | Action:
-Clear process recorded in meeting minutes. -Well organized. Especially the available working schedule in 4th Aug minutes, it is a very direct and efficient action!! -Explicitly roles and responsibilities. Listing everyone’s major is an approach to divide the corresponding roles in the project. But I suggest that you can decide it more specifically after few more hands-on works. Overall, your group did a very good job on recording the meetings which helps to monitor the project. | Tasks have been assigned more explicitly | Your group still has some technical questions about the project. So, I suggest -You can communicate with your clients individually, like Steve follows CD, Chris follows AS, etc. You might be able to obtain more information comprehensively, instead of spending so much time on one person and get less information for getting outputs. -You may ask some friends who have knowledge about parts which you have no idea. Such as the optical interface design. -You may ask the department in ANU that is responsible for the GSL about the GSL information. -Or you may offer some other proposals or design which you are capable of and in customers best interest at same time. | Will communicate with points of contact involved with the project as necessary. Point of contact has been assigned to minimise information fragmentation. | -Making more communications with the clients about approaching the project. -‘One-to-one’ contacting with customer, like Steve follows CD, Chris follows AS, etc. -Arranging weekly meeting with clients, and offering group updates to clients in time. -Making improvements on project’s status according to the clients’ feedback. Hoping my feedback can help! | Weekly meetings are being included into the schedule. Client expects us to be largely independent, this will be detailed.
They have detailed decision-making and detailed meeting minutes in the gitlab. According to their group meeting minutes, I find that not every member can give suggestions and recommendations, so I think that every member should participate in the discussion and give their own ideas. |  | They have detailed descriptions in risks which states that they get ready for the next challenges, but the resources and potential costs are blank. I noticed that they have clear current plans. I suggest that they can divide the plans into some small parts, and every two members or every three members in charge of one part. For example, two members check for changes in the project requirements and client requests, review conceptual design and understand its workings. The rest of the members do the remaining works. And after finish the current works, the team discuss together to give advices and recommendations. I think this method can work more efficient. | Project is being split as necessary, however this is still TBA, so arrangement is not complete. Group distribution is currently being actioned. | The team has a positive attitude to make the projects follow more smoothly. From the project concept report, they have doubts in development approach, so I suggest they should discuss more deeply to find the suitable development approach. And I also find that they have some acknowledge in the expectations of clients and stakeholders, but they are still not sure. So I think they should contact with the clients and stakeholders as soon as possible to thoroughly understand the expectations, since the expectations are the guides in the whole project. | Are working on clarifying this information.
You have clear evidence of decision-making. You can make a list to show your weekly tasks. And you need to know the expectation of your client in a certain period. The minutes of your meeting is very good. | No actionable feedback | I think that you need to know the resources,and potential costs of your project. I have noticed that your project will undergo three phases. I think that you can make a reasonable division of labor for each phase.such as you can divide your big group into 2-3 small groups. Since you from different majors, each member will do things what they are skilled in. It will helps you to improve your work efficiency. | Division of labour is now in the process for being distributed. | Maybe you need to make sure your development approach is continuous and the expectation of your stakeholders. Your teamwork is good. Share responsibilities for meeting agenda items and be sure everyone participates. | Participation will be detailed further in work log. Meeting contribution is a summary, not all inclusive.
Your repository is well organised and easy to navigate. However, it might help to include some indication in the README of where the most relevant documents are that we should look at. Perhaps before the next Audit you could dedicate a short paragraph to outlining which files have been focused on most since this audit, so that it is easy to see where you have made progress. | Included READMEs. Will look to include a description of relevant works from previous work period | I think that you need to know the resources,and potential costs of your project. I have noticed that your project will undergo three phases. I think that you can make a reasonable division of labor for each phase.such as you can divide your big group into 2-3 small groups. Since you from different majors, each member will do things what they are skilled in. It will helps you to improve your work efficiency. | Potential resource and cost requirements will be addressed in the coming week. Division of labour is being worked on. | Well done for your proactive approach to meeting stakeholders and orienting yourself with the project generally. You're setting yourselves up for a good semester. I like that you have begun by defining your scope within the Pro Forma. Obviously this document isn't finished yet, but it would be good to see a clearer description of what exactly you hope to deliver as the Preliminary Design. Going in to a little more detail about what this entails will help to orient those unfamiliar with the project and also help to show stakeholders that you have a solid understanding of what you are being asked to do. | We are producing a project summary document. Will further establish goals and expected deliverables.
Minutes contain a large amount of information, however this hasn't been summarised or really utilised as of yet. Clarifying content on the README would make the project clearer, allowing it to act as a full summary. | README has been clarified. Minutes already summarised | Outputs as of yet have been limited, with not much on the technical side. Breadth of topics covered is larger, however these are only covered to a basic extent. Summaries of the technical goals of the project would improve this. | Will expand the coverage of documents with summaries. | Approach is well done, with regular contact between the group, tutor and stakeholders. Acting on feedback was present, however could have been made clearer (eg. justification for doing certain tasks, if this is relevant) | Will clarify decisions clearer.
Project is clearly organised, and there are files and folders dedicated to recording meetings, decisions, tasks, and goals. However, some of these files, such as the Project_Status and Current_Task, as well as weekly summary, appear to be redundant - perhaps these documents could be consolidated into a single running file, or they could be made more specific - an additional, related problem is that there is no specific description of what each of the documents inside the folders contains - the folders themselves are described, but in some cases not their many contents, and the name alone does not give enough detail. | Removed redundant files. Included READMEs in subfolders detailing files | There do not appear to be many technical outputs yet at this phase of the project - most of them seem to relate to the administration and organisation of the project, with only the pro forma and project requirements, which is mostly review on the work of the previous team, as technical outputs so far - the group should more quickly work on the project requirements and producing a project schedule in order to actually allow the project work to begin. | A portion of this work had already been completed. We will work on making this information more clear to the auditors. Work will be becoming more technical in the coming week. | The team appears to have produced a reasonably continuous development approach outlined in the pro forma through the phases, but this is yet to be implemented -> the many governance files and folders need to be organised and updated for this approach to succeed. In addition, there has been a significant amount of engagement with the main stakeholder, but the group should also seek out other stakeholders related to the project and engage with them. Finally, the team has been very responsive to feedback in tutorial session and lectures, adding files to cover missing areas, even if in some cases they are not fully used, such as many of the documents in the Current_Status folder. | Cleaned up repository
Formalise team roles and responsibilities. | Completed | At this early stage no outputs valuable to the client have been delivered. To fix this, project scope and schedule need to be finalised. | Pro-forma details this information. | The team is still at the forming stage, so to improve communication and set a professional team attitude more team activities (meetings, tutorials, etc.) are needed. | These have been planned, but not documented. Will update.
PG1: Decision making document was clear short and succinct and as the project is still in the initial stages there were no technical decisions that were make. Decisions such as who will chair meetings and secretary that will take minutes should be listed in the decision-making document addition to decision to use slack and gitlab. Minutes document clearly the decisions that were made throughout the project and who was involved in making them. PG2: Calendar, project status, deliverables, current tasks documentation all show evidence of organisation of the project. The calendar could be used to map out the semester and possible milestones to be met in addition to dates next to the project status to ensure they are up-to-date. How is the confidential information being communicated to the shadows? PG3: Minutes are very clear in addition to evidence of the slack channels being used and named accordingly. The deliverables that have come out of meetings are clearly listed in short dot points at the top making it easy to read. The previous groups documents and handover meeting makes it clear as to it building on it, but not clear as to the direction of the project, unless read in the minutes. Creation of client’s comments, or requirements, or project goal should be listed in a new document in the client interactions folder. | Will add milestones to Calendar. Will include information about confidential documents. | PO1: Two documents on the technical research conducted in the field have been put in an odd location and named ‘files’, recommend moving to a more logical location. This does reveal the technical understand that is required prior to commencement of the project, in addition to the complex nature of the handover files. The initial concept report also has technical information in it, but should be polished up and simpler so that all audiences such as shadows are able to read it. Also, considering moving the clients vision into another document as well. PO2: Meeting etiquette taking and email correspondence is evident. There is no evidence of long term project planning further than the colander document and readme file with group member skills that was created. Milestones, Gantt chart, and other project documentation would be highly recommended. PO3: As projects are in their preliminary stages it is impressive that the team has had correspondence with the: previous team for a handover in an extensive meeting; client through organised emailing and tutor and course convenor communication. The documentation handover was rapid in addition to discussions of NDA and IP contracts. | Respository has been reorganised. Will include a project summary to give auditors a better understanding. Project documentation is being expanded to cover mentioned documents. | PA1: There is no information on the development approach as there is a lot of information from the previous team that needs to be synthesised. The information that is available is from the handover documentation and the weekly time spent at AITC. It is still a project design phase for a preliminary design for our client. Making this more explicit would be beneficial. PA2: Email correspondence is evident and a meeting agenda was made by the client, making it clear that the client is interested in discussion. The contact list is evidence of other appropriate stakeholders that are involved in the project and their respective roles and responsibilities. PA3: Minutes are detailed and comprehensive, add chair and secretary and meeting duration to enhance professionalism. PA4: Handover from previous team is great to see, team meetings are valuable and all team members present as attendance is taken and skill description in the readme file, but definitive role descriptions should be decided upon soon. PA5: We are acting on feedback from our tutor and client, which is evident in the meeting minutes. It is still in the initial stages of the project and thus there is not much feedback to respond to. | Most components have been updated as of week 3.
One aspect that could be improved regarding organisation would be to develop a spreadsheet containing the current responsibilities and tasks for each team member. This would contain current and completed tasks undertaken by team members, and would ensure that team member time is being used efficiently. It is also difficult to trace actions since they are largely contained in the minutes documents that must be downloaded and opened in word. One recommendation would be to include a readme file in the respective folders that outlines key actions to be undertaken that have resulted from the minutes. | Taks complete | The only technical document that is available is the draft pro forma. While much of the technical work has not been completed due to lack of access to facilities (which is understandable), some other preliminary documents should be produced. This includes a risk assessment for the project, any project constraints and the identification of potential costs and who will bear them (e.g. transport costs to Stromlo). | Further work will be completed in the coming week. Some documents have already been completed. Potential costs are covered by client, this will be noted. Costs to the team members are assumed to be funded by team members and largely irrelevant - Stromlo is the place of work, and it is assumed that group members can get there. | It is difficult to assess team member contribution from the repository. I would recommend documenting the tasks that have been completed by specific team members, which would be particularly useful for future teams so they know who to contact if there are issues. This could be done through a simple activity log that is completed throughout the week as the completes tasks. There does not appear to be regular meetings with stakeholders and I would recommend arranging such a meeting, even if it is a simple 30-60min catch up with the client every two weeks. This would allow the team to confirm if they are on the right track and if what they are doing is useful.
Somehow the risks, constrains and stakeholder analysis is initiated but not completed before the audit. We need to go through the audit criteria next time first. | Will go through audit criteria next audit. | The technical depth requires further investigation into client's requirement and then we need to design specific mechanisms using our mechanical and electrical expertise. There are sufficient technical documents describing GSL, but no evidence that team members have fully understood that. | We will produce project summary document for auditors that is easy to understand. | We didn't get the full version of previous work which is vital for proceeding the project until the last day of this week. This can be avoid if we have regular contact with the previous team members. | Regular contact can be established with the previous team due to them working onsite, and one being our tutor.
in my opinion, the governance of this group have problems with: 1: a file named decision-making can be found in the audit. however, i think the content is more like a schedule. i advised just place the decision that will affect the project in this file. 2: the files are named appropriately which is good. but the organization seems not tightly enough. it's not easy to find out what i want to see. try to delete some empty file and merge some files. 3: the schedule of this group seems very roughly. seems don't have a plan for the project. maybe have a group meeting and think about the milestone of the project and estimate the finishing time. 4: besides, this group uses gitlab for sharing. however, i can't see the world, excel and some other kind file online, hence i need to download it which is very complicated. (ps. maybe is just i don't know how to use gitlab) | Will be more explicit with project planning. Repository is being restructured to improve logical flow and readability. Schedule is being updated as project is clarified. Gitlab is the expected method, and the inability to display certain files is due to the software. Unfortunately we can't addressed that. | 1:first of all, as a concept audit, i didn't find the understanding of the group to the project. maybe create a file named project concept. 2: can't find the client requirement of the project. if not because of the mess of the files, then make a discussion with the client, get a clear mind of what he wants and record it. 3: in my opinion, the output is not appropriate enough. the concept audit should show us how the groups understanding the project. write a file about project concept, a file about client requirement, a file about technical challenges, a file about how to solving the problem should be more appropriate. | See above. Will also direct to relevant files better. | 1: the audit shows that the group has a good contact with stakeholders. however, for the client communication, i think there is no need to place the copy of the e mail of client. 2: the acting on feedback is good. the feedback of each meeting can be found in the gitlab. 3: the approach of the project is not clear and the contribution of each team member is not clear. maybe can write a working log to record what they do. 4: really recommend to use a google drive or a onedrive for sharing, since has much files can't be opened in gitlab directly. | Client emails are included for information that they provide, such as indicating meetings or communication which is required for the course. Will correspond with the client and convenor to see if these are necessary, however this form of document keeping is expected to be valuable for traceability. Are developing a work log document to detail work completed by group members. Gitlab was recommended for the course. It is intended to make this more deadable by using PDFs and READMEs. Excels have been left as is, which will require the viewer to download.
This group has good content. It contains clients communication, current status, meeting recode, previous team work, project artifacts and project requirement. It means they think about every aspect of the project and would like to show us. However, I believe there are two things they can improve in the future work. First, gitLab contains too many files under seven main file. It is hard to governance. And I found that a lot of records only has 3 or 4 sentences. My advice is to delete the useless files and merge them into one document. It can improve the efficiency of the work. Second, in the work schedule, I cannot see any information and details of work. I think a plan should contain the detail of the work in every period and who will respond to the project. | Respository has been neatened. Work schedule is being updated gradually. | From previous team work, I have a basic understanding of the project and the progress. I think if the group is an entirely new group without previous team member, they should have their project concept. It shows how they understand this work and what they need to do in this project. At the same time have a meeting with the previous group if it is possible. Second, they can upload a file which contains the knowledge they have learned, and they are going to learn. Meanwhile, share useful video and file to the team members. Only when the group have the related skill, can they have better project outputs. | Previous group meeting already occurred. Summary was not completed due to lack of value to the client. A form of a summary will be completed, as stated above. | I think they have done well in PA1,2,3 and 5. But they should work on the team collaboration. From the parts contributors in gitlab, I can see that Stephen Patrick Lonergan have 130 commits from 4 August to 6 August. The rest of group members are below 30. It also shows that Wen Jie Mu have done the work from 04 August to 10 August. The rest of group members only shows in a short period. Every team member should join the meeting and do the work with others. They can build up a file. Every member can write their opinions and upload the file. In this way, everyone can see ideas from others. This method also avoids one problem. If someone cannot join the meeting, other group members still know his opinions. | This was due to an issue with the SSH of the repository, which has since been addressed. The number of commits is not indicative of thework completed.