## Sheet1
Risk | Severity/Likelihood | Areas Affected | Mitigation
Uncertainty about ANU laser specifications | High Severity, Likely | Design of the mounting, timeframe of the project | Continuously update information, flexible designs
ANU laser being cancelled | Critical Severity, Unlikely | Potential cancellation of entire project | Make sure design is still useful for other laser
Scope creep | Minimal Severity, Unlikely | Entire project, timeframe, resources | Recognising limitations, sticking to timeframe
Transportation problems | Low Severity, Likely | Ability to access the work site | Planning alternative transport, making work accessible
Information leaks | High Severity, Unlikely | IP of the project | Proper handling of information